## Overall advance in FCPF process
Inter-American Development Bank (BID) -Guatemala
PROGRESS MONITORING REPORT (PMR) FOR THE FOREST CARBON PARTNERSHIP FACILITY (FCPF)
I. Describe progress in how the Grant activities are being coordinated with other REDD+ related initiatives, included those funded by others:
The process of constructing the REDD+ Strategy includes the civil society, as well as the private and public sector. A series of workshops and meetings are being held as to coordinate the Grant activities with those of other international donors: early socialization process; social and environmental safeguards; reference emission scenarios; MRV system for emissions, multiple benefits, other impacts, governance and safeguards; ER strategy regarding Improved Cookstoves and sustainable fuelwood production. Coordination has been established with the following institutions: USAID, RainForest Alliance, Del Valle University, Sotzil Association, TNC, the Nature Defenders Foundation, CARE, Terra Global Capital, IUCN, CATIE, UNDP, REDD+/SES, Global Alliance.
II. Describe any important changes in the technical design or approach related to the Grant activities:
(a) National consultation and participation process: , Sotzil Association (Indigenous organization) will facilitate the process in coordination with the National Forest Institute and the National Council for Protected Areas. (b) The SESA, ESMF and FGRM elaboration will be integrated in one consulting procurement. (c) Reference emission scenarios, will be developed under the Carbon Fund Methodological Framework and Jurisdictional Nested REDD+ Framework (JNR/VCS) as approved at a high level by the authorities of the GCI group.
III. Describe progress in addressing key capacity issues (implementation, technical, financial management, procurement) related to this Grant:
Several training events have been held with the participation of the private and public sectors, as well as indigenous groups and the civil society. The events were related to: (a)safeguards, targeting the National Social and Environmental Safeguards Committee (CNSAS); (b)reference emission scenarios under the VCS JNR Framework , with participants from the Interagency Group on Forest Monitoring and Other Land Uses (GIMBOT) and the REDD+ Implementers Group (GIREDD+). In terms of (c) financial management and procurement, an Operations Analyst from IDB provides support to the Project Executive Unit (Coordinator, Finance Specialist and Procurement Specialist).
IV. Describe progress in addressing social and environmental issues (including safeguards) related to the Grant. Is the SESA conducted in accordance with the Common Approach? Is the ESMF prepared in accordance with the Common Approach?
Nothing to report
V. Describe the progress in stakeholder consultation, participation and disclosure related to this grant.
Nothing to report

## Progress Monitoring Report
Inter-American Development Bank (BID) -Guatemala
PROGRESS MONITORING REPORT (PMR) FOR THE FOREST CARBON PARTNERSHIP FACILITY (FCPF)
Operation number of grant: | GU-T1194
Reporting period / Fiscal year: | 01/2014-12/2014
Last update: | N/A
A. OPERATION BASIC DATA
Operation number of grant: | GU-T1194
Recipient country: | Guatemala
Executing Agency (EA): | Ministry of Environment and Natural Resources
Team Leader: | Omar Samayoa
Grant start date / end date: | 04/2014 - 04/2018
Overall project stage: | Implementation
B. FINANCIAL DATA IN USD
Approved project cost (IDB) total: |  | 3800000
Accumulated disbursements (IDB) total until dd/mm/yyyy (report date): |  | 68000
Planned disbursements (IDB) for report period 01/01/2014 to 31/12/2014: |  | 68000
Accumulated disbursements (IDB) for report period 01/01/2014 to 31/12/2014: |  | 68000
Outstanding commitments: |  | 854400
Accumulated administrative costs (IDB) total until dd/mm/yyyy (report date):
Accumulated administrative costs (IDB) for report period 01/01/2014 to 31/12/2014:
C. OVERVIEW
Operation objectives:
The main objective of this operation is to support the Goverment of Guatemala (GoG) developing the National Strategy for Emission Reduction of green house gases (GHG) from deforestation and forest degradation.
Overall progress from 01/01/2014 to 31/12/2014 with regard to achieving operation objectives
• Component 1: capacity building activities performed. Terms of reference written for the national consultation and participation process. • Component 2: Identification of policy instruments which support REDD+ activities. Terms of reference (ToRs) have been written for: (a) the Benefit Sharing Mechanism; (b) the Assessment of Land Use, Land-Use Change Drivers, Forest Law, Policy and Governance; (c) Characterization of wood market; (d) Systematization of the policies and forest governance Framework; (e) Preparation of the National REDD+ Strategy; (f) Preparation for the implementation of carbon enhancing activities; (g) Preparation of SESA, ESMF and FGRM linked to the national consultation and participation process of the Strategy. • Component 3: Coordination for the development of the Reference Emission Scenarios under the Carbon Fund Methodological Framework and Jurisdictional Nested REDD+ Framework (JNR/VCS) for each REDD+ modality in the 5 REDD+ regions, covering the whole country. • Component 4: Coordination regarding the MRV system has been undertaken. The MRV system will include monitoring and information process for GHG emissions, multiple benefits, other impacts, governance and REDD+ safeguards; ToRs have been updated.
Overall progress from 01/01/2014 to 31/12/2014 with regard to implementation of grant financed activities
In October, 2014, eligibility conditions for the first disbursement were fulfilled. The process of elaboration of ToRs and equipment requirements for the priority short-term actions were concluded: SESA-ESMF, FGRM; national Consultation and Participation process; equipment for MRV system and development of Reference Emission Scenarios; institutional focal points and technical SIG staff. Moreover, there have been several training workshops with stakeholders to coordinate the execution of the Readiness process. A project Coordinator, a Financing Specialist and a Procurement Specialist have been hired in the Executing Agency, the Ministry of Environment and Natural Resources (MARN). 4 focal points (one per each institution of GCI) have been hired, and they are coordinating activities with Executing Unit of MARN. The task force to prepare the reference scenarios has been hired (10 GIS experts).
D. OPERATION COMPONENTS AND IMPLEMENTATION PROGRESS
Overall operation outcome: | National REDD+ Strategy
Observations on outcome achieved from 01/01/2014 to 31/12/2014:
Milestones
Indicators
Components
Component: | 1. Organization and Consultation
Activities: | i) National REDD+ Readiness Arrangements; ii)information disemination and early dialogue; iii)Consultation & Participation process
Status of planned and so far achieved output: | National arrangements to manage and coordinate the REDD+ readiness activities in progress
Status of planned and so far achieved milestones:
i) a) Reactivation of the Interagency Coordination Group (GCI) at a political level; b) Joint planning and coordination of the activities; c) Harmonization of funding from different donors in the readiness phase; d) REDD+ supporting groups articulated to the development of the Strategy (CNSAS; GBByCC; GIMBOT), e) Execution Unit formed and administrative structure developed, f) Forest Governance structures identified for the preparation and dissemination of the socialization plan with cultural and gender relevance, and g) Actualization of ToR´s for the national consultation and participation process. ii) Early socialization with stakeholders’ governance platforms being coordinated with Association Sotzil, UICN and USAID: training of 185 regional institutional staff, local community of the REDD+ activities and in process of training more local community stakeholders nationwide.
Status of planned and so far achieved indicators: | On going multiple stakeholders participating in consultations and the design of the National REDD+ Strategy.
Identified risks and mitigation measures: | Risks |  | Mitigation measures
| Political or community opposition. |  | Workshops on full and effective participation and consultation at all stages of the project so that all responsible parties and stakeholders actively involved;
| Weak local management capacities |  | Support for institutional strengthening according to the demands of each component of the strategy. Coordination with each institution for involvement of key staff in training on the different components .
| Limited participation of vulnerable groups such as indigenous peoples , communities related to forest management , among others. |  | Use of governance structures that allow the participation of vulnerable groups such as Forest Roundtables, Network Beneficiaries PINPEP , the creation of the National Committee of Environmental and Social Safeguards involving Multiple actors.
| Limited participation of key stakeholders within the actions to reduce emissions |  | Meetings with key stakeholders who have limited participation in REDD + actions to socialization in the direct and indirect benefits of such actions in their portfolios of work, and the legal rules that sustains and must be met.
Component: | 2. REDD+ Strategy
Activities: | I) Assessment of Land Use, Land Use Change Drivers, Forest Law, Policy and Governance; II) REDD+ Strategy Options; III) Social and Environmental Impacts.
Status of planned and so far achieved output:
Key drivers of deforestation and forest degradation identified; define REDD+ strategy options; develop a platform for consultation, socialization and development of the Strategy for forestry incentive activities; define a Governance and Institutional framework and ensure compliance with the Common Approach (SESA, ESFM and FGRM).
Status of planned and so far achieved milestones:
REDD+ activities and causes and drivers of deforestation and degradation defined in ER-PIN, ToRs already updated for “Assessment of Land Use, Land-Use Change Drivers, Forest Law, Policy and Governance”. This is expected to be done during 2015 and MARN is responsible for the bidding process; ToRs prepared for: a) Characterization of wood market, Design of the benefit sharing mechanism(s), b) Systematization of the policies and forest governance Framework, Preparation of the National REDD+ Strategy, c) Preparation for the implementation of carbon enhancing activities, d) Preparation of SESA, ESMF and FGRM linked to the national consultation and participation process of the Strategy.
Status of planned and so far achieved indicators: | On going: Aproval of the REDD + strategy document by representative sectors
Identified risks and mitigation measures: | Risks |  | Mitigation measures
| Difficulty to harmonize forest sector policies with policies that promote deforestation. |  | Formation of structures for Governance and Participation on both the forestry sector institutions and the ones linked to deforestation drives .
| Lack of coordination among participating actors. |  | Workshops or coordination meetings; Governmental Agreement to institutionalize the coordination and thematic groups that support the development of the National REDD+ Strategy (Climate Change Act, Article 20)
| Strategy is not anchored to the institutions or government policy tools |  | Mainstreaming the National REDD+ strategy into the policy tools and goverment action plans, and the priority actions of institutions and other sectors.
| Decreased level of executor commitment. |  | Progress reports and outcomes of the project, addressing at the same time with the requirements agreed at international commitments made​​. Follow the mandates calls of the Climate Change Law Act .
Component: | 3. Reference Emissions Level
Activities: | Develop National Reference Emissions Scenario
Status of planned and so far achieved output: | Elaboration of the ToRs for the development of the strategic baselines, analysis of carbon dynamics, hiring of 10 technicians on GIS to streamline the development of the National Reference Emissions Levels, and purchase of hardware and software for the elaboration of the reference emission scenarios.
Status of planned and so far achieved milestones: | I) Reference emission scenarios are being coordinated for the 5 REDD+ regions following the requirements of the Methodological Framework of the Carbon Fund (advancing of 30%). A working plan for the development of the National Reference Emission Scenario was developed. II) Ten GIS technicians hired and supporting GCI and GIMBOT for the development of the Reference Emission Scenarios; ToRs ready for Harmonization of REDD+ projects with national accounting framework; SIG technical equipment bought.
Status of planned and so far achieved indicators: | On going: At least 80% of the country has a GHG emission Linebase developed.
Identified risks and mitigation measures: | Risks |  | Mitigation measures
Component: | 4. Desing of the National Monitoring System
Activities: | National Forest Monitoring and Information System for GHG Emissions
Status of planned and so far achieved output: | Establish a governance scheme of the national system of monitoring GHG emissions for REDD+
Status of planned and so far achieved milestones: | I) Conceptualization of the National System of MRV by technical groups and Interagency Group on Forest Monitoring and Other Land Uses (GIMBOT) II) ToRs made and updated for the National Monitoring and Information System for GHG emissions, multiple benefits, other impacts, governance, and REDD+ safeguards.
Status of planned and so far achieved indicators: | On going: The country has a system for monitoring GHG emissions and non-carbon benefits and governance, to generate reports according to requirements of the UNFCCC. Monitoring System implemented and issuing important reports.
Identified risks and mitigation measures: | Risks |  | Mitigation measures
| Dispersion of the country's institutionality for the generation of respective information for the monitoring and information system |  | Governmental / Ministerial Agreement that allows coordination among public institutions

## FCPF Common Approach
Implementation of the FCPF Common Approach
Planned environmental and social sustainability standards for the whole project duration: Planned environmental and social sustainability standards for the whole project duration: IDB's social and environmental safeguards and policies will be applied, in accordance to the FCPF Common Approach.
Applied environmental and social sustainability standards 01/01/2014 to 31/12/2014: The environmental and social standards (policies) were taken into account during the elaboration of the terms of reference of all the activities within the four components of the Strategy.
Description of planned stakeholder engagement activities during the whole project duration (incl. timing and target groups): for 2015 and early 2016, the the main activities are: (i) development of the consultation and participation methodology according to the FCPF, UNREDD Program, Common Approach and ILO 169 guideliness, (ii) systematization of consultation and participation process; (iii) early socialization process for the political level; (iv) complete consultation and participation in at least two REDD+ regions.
Description of progress in stakeholder consultation, participation and the Feedback & Grievance Redress Mechanism for Readiness (FGRM) on the country level related to this grant: several workshops and meetings were held with multisectoral participation for the preparation of the four components of the National REDD+ Strategy. Articulation of the thematic groups for the development of reference emission scenarios, MRV system, benefit sharing mechanisms, among others.
Description of progress of SESA until 01/05/2015 (report date) and its addressing social and environmental issues (including safeguards) related to the grant. Is the SESA conducted in accordance with the Common Approach?: ToRs for SESA, ESMF and FGRM are collated in a single consultancy; bidding process is on going.
Description of progress of preparation of ESMF until 01/05/2015 (report date). Is the ESMF prepared in accordance with the Common Approach?: Terms of reference were elaborated for SESA, ESMF and FGRM, aligned with the requirements of the Common Approach.
Description of the application of FCPF Guidance on Disclosure of Information until 01/05/2015 (report date): All documents that have been generated under the framework of the development of the National REDD+ Strategy are public access and can be found not only at IDB webpage (http://www.iadb.org/en/projects/project-description-title,1303.html?id=GU-T1194) but also at institutional goverment webpages such as the one of the Minister of Environmental (MARN), the National Forest Institution (INAB) and the National Council for Protected Areas (CONAP); this also supported by the Transparency and access to informacion La Act, 57-2008. As well, at the Minister of Environmental (MARN) webpage, it has been created an specific sub-portal for the National REDD+ Strategy where it can be found all the information about the readiness phase and the advances to access to the Carbon Fund payments; all the documents related to the Preparation Fund and the Carbon Fund, and including the legal framework that supports the strategy, and the advances on the REDD+ projects and the results of workshops, meetings and jointly planning with multisectoral stakeholders participation for the preparation of the four components of the Strategy, are public.

## PMR disbursements
DISBURSEMENT SUMMARY IN USD
Approved project cost (IDB) total: |  | 3800000
Accumulated disbursements (IDB) total until 31/12/2014 (report date): |  | 68000
Planned disbursements (IDB) for report period 01/01/2014 to 31/12/2014: |  | 68000
Accumulated disbursements (IDB) for report period 01/01/2014 to 31/12/2014: |  | 68000
Outstanding commitments: |  | 0
Compromised (contract is signed) and/or already disbursed money for project-specific activities (not including pre-excecution and pre-implementation activities)
TC number | Consultancy (Title of consultancy, name of consultant) | Objective of the consultancy | Component(s) supported by the consultancy | Contract date (dd/mm/yy) | Contract value in US$ | Notes & Comments
1 | Consulting 3 - Eight GIS techicians ( two for each GCI institution x 24 months) | Technical support for the four GCI institutions at their SIG directions in order to develop the products required in the components 3 and 4: national reference emissions scenarios and the national MRV system. | 3 and 4 | 2015-02-10 | 288000
2 | Consulting 5 - Four technical focal points (one for each institution GCI x 42 months= annual USD60,000 c/u) | Technical support for the climate change units at de GCI institutions for the preparation of the National REDD+ Strategy. | Executing Unit | 2015-02-02 | 252000
3 | Consulting 6 - Coordinator (48 months) | Specialst at the Minister of Environmental (Executor) to be in charge of the coordination of the development of all the products of the four components of the National REDD+ Strategy which are being preparating with all stakeholdes and other support gruops. | Executing Unit | 2014-11-25 | 120000
4 | Consulting 6 - Financial Specialist (36 months ) | Specialist of public and multilateral financial process to help with the administrative and financing activities concern to the preparation of the National REDD+ Strategy. | Executing Unit | 2015-02-02 | 97200
5 | Consulting 7 - Procurement Specialist (36 months ) | Specialis for public and multilateral procurment process to asssess the coordinator and financial specialist for the administrative and financing processess of the preparation of the National REDD+ Strategy. | Executing Unit | 2015-02-02 | 97200
TOTAL compromised for 2015 |  |  |  |  | 854400
[6 empty] | Compromised money (US$) of operation | Percentage of comprised operation funds | Total amount (US$) of operation
[6 empty] | 854400 | 22.48% | 3800000
Mid-term report due to the date when 50% of operation's funds (1.9 Mio) are compromised.

## Outlook
Brief Description with commitments and plans for 2015: The following table shows the activities planned per component as well as their objective, expected date and costs for 2015.
TC number | Expected consultancy (Title of consultancy, name of consultant) | Objective of the consultancy | Component(s) supported by the consultancy | Expected contract date (dd/mm/yy) | Contract value in US$ 2015
1 | Consultancy 1 - Implementation of the National Consultation and Participation Plan with stakeholders of the National REDD+ Strategy | Design and implement the methodology for the national consultation and participation process under the FCPF, ILO 169 and Common Approach guidelines, make an early socialization of the National REDD+ Strategy and complete the national consultation and participation process at least in 10% of the country. This includes: (a) the Desing of the mediation material, and (b) the design and print materials needed. | 1 | 2015-02-15 | 700000
2 | Consulting 2- Preparation of SESA, ESMF and MAR | Design the Common Approach tools in coordination with the respective goverment entities and aligned with the national consultation and participation process. | 1 | 2015-02-15 | 200000
3 | Goods 1: SIG Technical Equipment | Equipment that all 8 technical SIG will need so they can help the GCI institutions for the elaboration of the REL and MRV system. | 3 | 2015-03-10 | 25000
4 | Goods 2: Institutional strengthening for CONAP and INAB, for Reference Scenarios (purchase of software and hardware for baselines and MRV) | Equipment needed for the GCI institutions like hardware and software for the elaboration of the methodologies and emission base lines for deforestation, degradation and enhancing carbon stocks, and also for the MRV system. | 3 | 2015-06-29 | 275000
5 | Consulting 3 - National Monitoring and Information System for GHG emissions, multiple benefits, other impacts , management and the REDD+ safeguards. | Design and implement at a first stage the national monitoring and information system for GHG emissions, multiple benefits, other impacts, management and the REDD+ Safeguards. | 4 | 2015-04-03 | 300000
6 | Goods 3: Executing Unit equipment | Computers, software, hardware and other goods needed for the establishment fo the excecuing unit of the project. | Executing Unit | 2015-03-10 | 30000
7 | Workshops , trainings , meetings | To finance several workshops through 2015 with multisectoral participation (public sector, private sector, NGO´s, academia, Indigenous People and other stakeholders), for the preparation of the four components of the Strategy incluiding jointly planning workshops. | 1, 2, 3 y 4 | 2015-06-24 | 100000
TOTAL EXPECTED compromised amount for the end of 2015 |  |  |  |  | 1630000
EXPECTED Compromised money (US$) of operation 2015 | Compromised money (US$) of operation 2014 | EXPECTED Percentage of comprised operation funds | Total amount (US$) of operation
1630000 | 854400 | 65.38% | 3800000