## Overall advance in FCPF process
Inter-American Development Bank (BID) -Peru
PROGRESS MONITORING REPORT (PMR) FOR THE FOREST CARBON PARTNERSHIP FACILITY (FCPF)
I. Describe progress in how the Grant activities are being coordinated with other REDD+ related initiatives, included those funded by others:
The National Forest Conservation Program for the Mitigation of Climate Change (Programa Nacional de Conservación de Bosques para la Mitigación del Cambio Climático - PNCBCC) is the executing unit of the R-PP in Perú. At the request of the Ministry of Economy and Finance, the PNCBCC began the preparation of a strategic document describing how the different initiatives implemented by the PNCBCC complement each other, and how these initiatives are aligned with forestry-related programs and projects that are being implemented by other public entities. This analysis seeks to enhance synergies among initiatives and identify areas that require more attention. Initiatives that are being mapped include those that are either under design or under implementation. Some are financed by the public treasury, although the large majority are funded by international cooperation. The strategic document also describes how the objective and mission of the PNCBCC is aligned with the country's environmental policy instruments.
II. Describe any important changes in the technical design or approach related to the Grant activities:
During the time that has elapsed between the approval of the R-PP by the PC and the signature of the Cooperation Agreement by the Bank and the Government, other sources of international cooperation have contributed to advance in the implementation of activities that were originally planned to be financed by the R-PP grant. Therefore, some adjustments had to be made in the annual operational plan in order to build on the progress that was made so far. For instance, some of the studies included in Component 1 (Organization and Consultation) such as the analysis of institutional arrangements and legal framework required for the implementation of REDD+. R-PP will complement these studies, but will mostly focus on the implementation of the Stakeholder Involvement Plan. With respect to activities planned for Component 2 (REDD+ Strategy Preparation) KfW has been financing studies to assess land-use change and identify drivers of deforestation in different areas of the Amazon. Therefore the R-PP will finance similar studies in regions that have not been covered yet. The R-PP will also support the consultation process of the REDD+ National Strategy (the government has already produced a draft document) and its publication. With respect to Component 3 (Reference Scenario) KfW is currently supporting studies that will help the government define a national reference scenario. The R-PP will therefore support the events required to agree on the reference scenarios with stakeholders with the assistance of international experts. R-PP will also provide stakeholders (especially regional governments) with training on the methodological aspects of refrence scenario definition. Regarding Component 4 (Development of a National Forest Monitoring System) the government is producing the official report on historic deforestation, as well as the vegetation map, with the support from Moore, KfW and OTCA. R-PP is therefore planned to support a) the study to institutionalize the National Forest Monitoring System (NFMS), b) provide technological support for the implementation of the NFSM; c) support the development of a real-time monitoring system; d) develop a short-term deforestation risk model; e) support the development of a web tool for information sharing; and f) support the development of a safeguards information system.
III. Describe progress in addressing key capacity issues (implementation, technical, financial management, procurement) related to this Grant:
The Bank performed an institutional capacity assessment of the PNCBCC, which included the evaluation of the following systems: administrative organization, personnel administration, activities programming, goods and services administration, financial administration, internal control, and external control. The institutional capacity assessment found that PNCBCC meets the Bank's requirements to be the executing agency of the R-PP technical cooperation. The executing agency has also made progress towards meeting the conditions required for the first disbursement. One of the conditions that was met was the creation of the Project Coordinating Unit within the PNCBCC, through an Executive Resolution from the Ministry of Environment. Another condition met was the creation of the Steering Committee for the R-PP technical cooperation, which was convened in the month of August. This Committee, chaired by MINAM, includes representatives from the Ministry of Agriculture and Irrigation, the Ministry of Economy and Finance, the Ministry of Culture, and the Regional Governments. With respect to the condition of setting up a project team (a coordinator and a procurement specialist), the PNCBCC began the selection process for the procurement specialist. The PNCBCC also sent a formal request to the Minsitry of Economy and Finance to open the accounts were the technical cooperationd funds will be deposited. The following documents were also produced during this period: Annual Operational Plan, Procurement Plan and Financial Plan (linked to the other two).
IV. Describe progress in addressing social and environmental issues (including safeguards) related to the Grant. Is the SESA conducted in accordance with the Common Approach? Is the ESMF prepared in accordance with the Common Approach?
Nothing to report
V. Describe the progress in stakeholder consultation, participation and disclosure related to this grant.
Nothing to report

## Progress Monitoring Report
Inter-American Development Bank (IDB) - Peru
PROGRESS MONITORING REPORT (PMR) FOR THE FOREST CARBON PARTNERSHIP FACILITY (FCPF)
Operation number of grant: | PE-T1294
Reporting period / Fiscal year: | 01/2014-12/2014
Last update: | N/A
A. OPERATION BASIC DATA
Operation number of grant: | PE-T1294
Recipient country: | Peru
Executing Agency (EA): | Programa Nacional de Conservación de Bosques para la Mitigación del Cambio Climático (PNCBCC)
Team Leader: | Eirivelthon Lima / Jaime Fernández-Baca (co-leader)
Grant start date / end date: | 05/2014 - 05/2017
Overall project stage: | Approved
B. FINANCIAL DATA IN USD
Approved project cost (IDB) total: |  | 3800000
Accumulated disbursements (IDB) total until 31/12/2014: |  | 0
Planned disbursements (IDB) for report period 01/01/2014 to 31/12/2014: |  | 0
Accumulated disbursements (IDB) for report period 01/01/2014 to 31/12/2014: |  | 0
Outstanding commitments: |  | 0
C. OVERVIEW
Operation objectives:
Support the Government of Peru in the implementation of the R-PP, which includes activities for the institutional arrangements and public consultation for issues related to REDD+, the preparation of the REDD+ national strategy, the development of national reference scenarios pf greenhouse gas emissions, support to the implementation of the national forest monitoring system, and support to the implementation of environmental and social safeguards.
Overall progress from 01/01/2014 to 31/12/2014 with regard to achieving operation objectives
Although implementation did not begin during this period, other sources of international cooperation have helped the government make progress towards operation objectives. This is described in section II of the previous tab. The operation plan of the technical cooperation has been adjusted to build on this progress.
Overall progress from 01/01/2014 to 31/12/2014 with regard to implementation of grant financed activities
Implementation did not begin during this period.
D. OPERATION COMPONENTS AND IMPLEMENTATION PROGRESS
Overall operation outcome:
Observations on outcome achieved from 01/01/2014 to 31/12/2014:
Milestones:
Indicators:
Components
Component: | 1. Organization and Consultation
Activities: | The implementation of the Grant activities did not start during the reported period
Status of planned and so far achieved output:
Status of planned and so far achieved milestones:
Status of planned and so far achieved indicators:
Identified risks and mitigation measures:
Lessons learned and recommendations:
Component: | 2. Preparation of REDD+ Strategy
Activities: | The implementation of the Grant activities did not start during the reported period
Status of planned and so far achieved output:
Status of planned and so far achieved milestones:
Status of planned and so far achieved indicators:
Identified risks and mitigation measures:
Component: | 3. Reference Emissions Level
Activities: | The implementation of the Grant activities did not start during the reported period
Status of planned and so far achieved output:
Status of planned and so far achieved milestones:
Status of planned and so far achieved indicators:
Identified risks and mitigation measures:
Component: | 4. Desing of the National Monitoring System
Activities: | The implementation of the Grant activities did not start during the reported period
Status of planned and so far achieved output:
Status of planned and so far achieved milestones:
Status of planned and so far achieved indicators:
Identified risks and mitigation measures:

## FCPF Common Approach
Implementation of the FCPF Common Approach
Planned environmental and social sustainability standards for the whole project duration: The UNFCCC REDD+ safeguards will be implemented (Cancún Safeguards). Peru will have to define how these safeguards will be addressed in the national context, through the policies, strategies and planes that the Ministry of Environment and other relevant sectors are developing, such as the National Strategy of Forests and Climate Change, the Forest and Wildlife Law, and the Safeguards Information System.
Applied environmental and social sustainability standards 01/01/2014 to 31/12/2014:
Description of planned stakeholder engagement activities during the whole project duration (incl. timing and target groups): The project will support the implementation of a Stakeholder Invelvement Plan, which includes a communications plan for the REDD+ activities, the organization of regional workshops for consultation of the National Strategy of Forest and Climate Change (i.e. the REDD+ Strategy), and technical support for strengthening the national and regional REDD+ roundatables, as well as the REDD+ Indigenous roundtables.
Description of progress in stakeholder consultation, participation and the Feedback & Grievance Redress Mechanism for Readiness (FGRM) on the country level related to this grant:
Description of progress of SESA until 31/12/2014 and its addressing social and environmental issues (including safeguards) related to the grant. Is the SESA conducted in accordance with the Common Approach?:
Description of progress of preparation of ESMF until 31/12/2014. Is the ESMF prepared in accordance with the Common Approach?:
Description of the application of FCPF Guidance on Disclosure of Information until (report date): The current state of the project is reported in the IDB website http://www.iadb.org/en/projects/project-description-title,1303.html?id=PE-T1294

## PMR disbursements
DISBURSEMENT SUMMARY IN USD
Approved project cost (IDB) total: |  | 3800000
Accumulated disbursements (IDB) total until 31/12/2014: |  | 0
Planned disbursements (IDB) for report period 01/01/2014 to 31/12/2014: |  | 0
Accumulated disbursements (IDB) for report period 01/01/2014 to 31/12/2014: |  | 0
Outstanding commitments: |  | 0
Compromised (contract is signed) and/or already disbursed money for project-specific activities (not including pre-excecution and pre-implementation activities)
TC number | Consultancy (Title of consultancy, name of consultant) | Objective of the consultancy | Component(s) supported by the consultancy | Contract date (dd/mm/yy) | Contract value in US$ | Notes & comments
1
2
3
4
5
6
7
8
9
10
11
12
TOTAL compromised |  |  |  |  | 0
[6 empty] | Compromised money (US$) of operation | Percentage of comprised operation funds | Total amount (US$) of operation
[6 empty] | 0 | 0% | 3800000
Mid-term report due to the date when 50% of operation's funds (1.9 Mio) are compromised.

## Outlook
Brief Description with commitments and plans for 2015: This year the first disbursment has been approved and the technical team has been hired. The plans for the next half of 2015 are therefore to start execution according to the financial plan. This includes activities in all 4 componentes. A detailed acount will be provided in the next report.